Gildersome Health Centre

Patient involvement action plan – March 2015

- Project Aims

The aim of our patient involvement work is to….. Promote and extend ways for patients to feedback to the practice and demonstrate how the practice has responded to patient feedback

- Issues

The following issues were identified through the patient survey, patient comments and discussions at the patient reference group:

| The issues are…. - A Female GP/ Salaried GP - Refurbishment of the Health Centre - Online Appointments and Online Prescriptions - Extended Hours |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Review of Last Year |  |  |  |  |  |
| - A Female GP - Update the waiting area - Reception Area - Lighting |  | All areas were discussed at the meeting on 3rd March 2015. We will continue to monitor over the coming 12 Months. For details please see the Patient Participation Report |  |  |  |

- Objectives

The issues identified will be addressed in the following ways:

| Issue/theme | Objective | Tasks | Task lead | Completion date | Outcome |
| --- | --- | --- | --- | --- | --- |
| Female GP/Salaried GP | To employ ASAP | Due to Dr Kaushal’s resignation from the Practice we will be advertising for a salaried GP with a view to partnership. In the coming 12 Months we will try to establish a permanent GP in Practice. | PM/GP |  |  |

| Issue/theme | Objective | Tasks | Task lead | Completion date | Outcome |
| --- | --- | --- | --- | --- | --- |
| Refurbishment of Health Centre | Update the premises | NHS Property Services will be discussing Refurbishments to the Health Centre and once it has been finalised we will plan to spend our money carried forward from last year to improve other areas. | PM/ PRG |  |  |

| Issue/theme | Objective | Tasks | Task lead | Completion date | Outcome |
| --- | --- | --- | --- | --- | --- |
| On-line appointments and On-line prescription requests | To promote and register patients for the new service | - Liaise with the PRG to test out the system prior to the go-live date - Promote the new service in house and on the web site, register patients and ensure on-line appointments are available. Train staff appropriately | PM/OM PRG |  |  |

| Issue/theme | Objective | Tasks | Task lead | Completion date | Outcome |
| --- | --- | --- | --- | --- | --- |
| Extended Hours | 12 hours per day, 3 days per week | From 7th April 2015 on a 12 Month trial period we will open the surgery for 12 hours per day 3 days per week. We will need to recruit another GP to share the workload. | PM/GP |  |  |