## Sheet1
William Fisher Medical Centre
Action Plan Resulting from March 2012 Patient Survey and PPG Meetings
Patient Priorities / Issues | Comments | Agreed Actions | By Whom | Target date | Completion Date
Provide phlebotomy services at the surgery, including INR | A restricted Phlebotomy services is available within the Practice on Thursday mornings. However, from patient survey comments not all patients are aware of this fairly recent addition to the Practice services. Patients who are aware require the service to be extended and to include INR tests | Better publication of existing services. PPG members to place Information regarding Phlebotomy Services in their local village news. | PPG - Phil Davies Althorne | 2012-04-01 | Included in May/June 2012 Issue of Althorne Village News
|  |  | PPG - Nancy Peters Southminster | 2012-04-01 | April 2012 issue
|  |  | PPG - Babs Owers Burnham-on-Crouch | 2012-04-01 | April 2012 issue
|  |  | PPG - Liz Wynn Mayland | 2012-04-01 | April 2012 issue
|  | Practice Manager to add details of available phlebotomy services to the Practice website. | J Gauntley | 2012-04-01 | 12th May 2012
|  | Improve phlebotomy services by adding and additional day when service is available and add INR blood test. | J Gauntley | 2012-04-01 | 12th May 2012
Improve access for patients who work and find it difficult to get appointments without taking time off work and losing pay. | From Patient comments not all patients seem to be aware of the Thursday evening late surgery. | Better publication of existing services. PPG members to place Info regarding Surgery Opening Times in their respective local village news. | As per PPG members above | 2012-04-01 | 12th May 2012
Improve locally delivered health services. | Provide as many local consultation, diagnostic and treatment services as possible, to avoid visits to Broomfield. | Practice to Provide 24Hr Blood Pressure monitoring. | J Gauntley | ASAP | Mid April 2012.
|  | The Hear and Help charity to established a drop-in clinic at the surgery on the third Tuesday of every . | J Gauntley | ASAP | 2012-07-01
|  | Ultrasound Scans to be performed in the practice or be available locally. | J Gauntley | ASAP | Ultrasound scans available by appointment at two GP practices located in Mayland & South Woodham Ferrers
|  | Work with commissioning groups and other local surgeries to acquire more local services. | Practice Manager and Partners | Ongoing
Improve appearance of the surgery reception and waiting areas (looking tired) |  | Arrange redecoration of the surgery with priority on reception areas and waiting room. | J Gauntley | ASAP | Redecoration commenced W/E 18th Nov 2012
Increase Virtual Patient Participation Group menbership. | A larger and improved demographic membership will permit cheaper and more efficient patient surveys utilising the practice website survey software. | Encourage membership of the Virtual PPG on the welcome page of the practice website | J Gauntley | ASAP | 2012-09-01
|  | Prepare and display posters to promote membership of the Virtual PPG | Amy Cooper | ASAP | Mid Oct 2012
|  | Group flyer is to be included in the flu jab notices to 1000+ patients | J Gauntley | 2012-10-01 | 2012-10-01