## Table 1
William Fisher Medical Centre
Action Plan Resulting from March 2013 Patient Survey and PPG Meetings
Patient Priorities / Issues | Comments | Agreed Actions | By Whom | Target date | Date Completion
Poor Paramedic and Ambulance response times to emergency calls in the Dengie. | The results of the 2013 survey indicate that 'The East of England Ambulance Service NHS Trust' is not meeting the governments, or, its own response time targets. The trusts own published average response times for the Mid Essex area has been on, or, just a few percentage points below target since April 2012 to date. However, this average conceals the true situation in rural areas, and in particular the Dengie. The first target is 75% within 8 minutes for category A calls. Our survey indicates 0% for an Ambulance, and 35% for a Paramedic. The second target Providing transport for 95% within 19 minutes. Our survey indicates just 8% of Ambulance meet this requirement. | PPG secretary and Jackie Gauntley to compose a letter of concern and forward to Andrew Morgan, the Interim Chief Executive of the East of England Ambulance Service NHS Trust, with copies to: - Dr Lisa Harrod-Rothwell, Chair, Mid Essex CCG, - Norman Lamb MP, Minister of State for Care and Support. - John Whittingdale. MP Maldon | Babs Owers, Jackie Gauntley | Apr-2013 | Letter was sent to East of England Ambulance Service May 8th 2013.
Jason Gillingham attend the PPG meeting held on 15th January 2014 to explain the actions being taken to improve response times (see minutes of meeting)
The survey indicates that some patients, in particular those that work, would like to be able to get appointments outside normal working hours. | Analysis of changes requested is as follows: Saturday mornings 38% Later Evening Appointments 28% Lunch time Appointments 22% Earlier Morning Appointments 9% | Practice manager and partners to investigate what improvements can be made to increase access to appointments outside normal working hours, beyond the one late evening opening currently provided. | Debbie Morley and Practice Partners. | Report by Feb 5th 2014 PPG Mtg. | Since there was such low demand for early morning appointments (just 9%) this was not considered a proirity.
Lunch time appointments have been trialed. Theses were filled but did not result in a decrease in demand at other times. These appointments also created problems by reducing the time available to do visits.
Overall, after evaluation, it was felt that the decrease in the time for visits impacted more on patients than the availability of lunch time appointments and therefore they were discontinued. The practice is still looking at ways of increasing appointments in the late evening and on Saturdays. Unfortunatly, appointments at this time have an incresed cost attached to them and funding is an issue. Also, anciliary staff are not keen to do them which makes staffing these surgery times difficult.
Booking appointments by telephone is frustrating at busy times, requiring repeat dialling due to being permanently engaged. | Survey indicates that a more modern telephone system would be preferred, which places caller in a queue and gives repeat messages indicating where a caller is in the queue. | Upon investigation, practice management considered a telephone system with call queuing, and queue position messaging to be too expensive. Management have chosen a new telephone system, with four incoming lines, which means that four callers at any one time will not have to keep redialing, but will receive the dialing signal and have to wait for reception to pick up the call. Any more than four callers at any one time will receive the engaged tone, and have to redial. However, callers will have to redial less frequently | Jackie Gauntly | Status report by May 2013 PPG Mtg. | New telephone system, installed on Jan 2014.
The new system offers a slight increase in the number of lines into the surgery (2 x 2) and replaces all the old telephones which were in urgernt need of upgrading. However, it does not offer call queuing which was requested by the PPG. This is again due to a funding issue. The new system cost £4500 and 'call queing' can only be added as an add on to the new system. Currently we are awaiting a quote for this add on. Another option which might help with the congestion on the phone lines is to add Direct Dial lines. This is a much cheaper option and would allow patient to dial in directly to areas such as Pharmacy. again we are currently waiting on quotes.
Patient criticisms received suggesting the reception area is looking tired. | Waiting room redecorated in Nov 2012. Other areas to be completed when funds allow. | Redecorate the reception area, foyer and corridor | Jackie Gauntly to organise. | ASAP | Redecoration of reception office and ground floor corridor completed in Jan 2014.
The Virtual Patient Participation Group (VPPG) membership currently stands at 85, which is not large enough, and is also not fully representative of the age demographics of the patient list. | The recent groups efforts to increase the size of VPPG membership have been quite successful. However, to get a reasonable return on any future 'website only' survey, the size of the virtual group needs to be larger. | PPG members to continue their efforts in the foyer, approaching visiting patients and persuading those with access to the internet to join the VPPG, with specific targeting of age groups that are not adequately represented in the current VPPG. | PPG members | Ongoing until at least 200 VPPG membership is achieved. | VPPG member recruitment session in foyer at PPG Awareness Week June 2013. VPPG Membership as of 13th Jan 2014 is 125.
|  | Reception to hand leaflet to under 50 age group of both gender, in particular those under 30 | Debbie Morley | Ongoing until at least 200 VPPG membership is achieved. | VPPG membership as of 5th March 2014 is 132.
Where patient requests for changes or additions to services cannot be achieved, it would be helpful if patients, outside the Patient Participation Committee, could understand the constraints preventing the practice from providing what is being requested. |  | Advise patients, either via a PPG, or, practice news letter, where there are significant constraints preventing the achievement of patient requests, despite the willingness of the practice to deliver patient requested improvements. | PPG & Debbie Morley | When applicable on issues being investigated as detailed above. | Draft PPG newsletter already drawn up by PPG Chairman to give feedback on PPG activity and what has been achieved following last years questionnaire. Newsletter to be available in the suregy and also on the surgery website.